## Agile Project Backlog
Agile Product Backlog
PROJECT DESCRIPTION
Learner's Academy, needs an online management system for back-office application with single administrator login. The system should keeps track of it's classes, subjects, students, and teachers in the school.
PROJECT BACKLOG
ID | As a | I want to | So that | Priority | Story point | Sprint Assignment | Status
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours | Hours | Hours | Hours | Hours | Hours
1 | Admin | Have a home page | Application should have a landing page | Must | 20 |  | Done
2 | Admin | Have a option to login | I can view the data | Must | 33 |  | Done
3 | Admin | Retrive the list of all Classes | I can see how many classes are there | Must | 33 |  | Done
4 | Admin | Retrive the list of all Students | I can see how many Students are there with respective classes | Must | 33 |  | Done
5 | Admin | Retrive the list of all Subjects | I can see how many subjects are there | Must | 33 |  | Done
6 | Admin | Retrive the list of all Teachers | I can see how many teachers are there | Must | 33 |  | Done
7 | Admin | Retrive one particular Teacher details | I can see the complete details of Teacher like name, age, email, gender, subjects and, classes | Must | 33 |  | Done
8 | Admin | Have a option to view Class Report | I can see thecomplete details of Class like class name, strength, subjects, teachers and, students | Must | 33 |  | Done
9 | Admin | Have a option to logout | I can logout | Must | 33 |  | Done
10 | Admin | Have a error page | All the errors will be handled | Must | 33 |  | Done

## Agile Sprint Backlog
Agile Sprint Backlog
SUMMARY
CHANGE IN SCOPE
| Original Story Points |  | 297
| New Points |  | .
| Total Points |  | 297
| CHANGE IN SCOPE |  | 0%
SPRINT BACKLOG
ID | Backlog task | Assigned to | Story points | New points? | Release | Status | Business value | Change management notes | Initial estimate
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours
1 | As a Admin, I should have a home page
1.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.4 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.5 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
1.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
2 | As a Admin, I should have an option to login, so that I can view the data
2.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
2.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
2.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
3 | As a Admin, I should have an option to view the list of all Classes.
3.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
3.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
3.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
4 | As a Admin, I should have an option to view the list of all Students with details like name, age, gender, email and, class.
4.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
4.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
4.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
5 | As a Admin, I should have an option to view the list of all Subjects.
5.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
5.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
5.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
6 | As a Admin, I should have an option to view the list of all Teachers.
6.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
6.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
6.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
7 | As a Admin, I should have an option to view the complete details of particular Teacher like name, age, gender, email, Subjects and, Classes
7.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
7.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
7.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
8 | As a Admin, I should have an option of Class Report. So that, I can see complete information about the Class like name, strength, no.of teachers, list of students, subject and respective teacher.
8.1 | Design the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.2 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.3 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.4 | Code the Database | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.5 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.6 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
8.7 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
8.8 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
9 | As a Admin, I should have an option to logout.
9.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
9.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
9.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0
10 | As a Admin, I should have a error page. So, that all the errors will be handled.
10.1 | Design the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.2 | Design the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.3 | Code the UI | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.4 | Code the Backend | Riyaz J | 5 | FALSE | 1 | Done | High |  | 5
10.5 | Test the functionality | Riyaz J | 3 | FALSE | 1 | Done | Medium |  | 3
10.6 | Push the code to GitHub | Riyaz J | 0 | FALSE | 1 | Done | Low |  | 0